PROJECT CHARTER

GENERAL PROJECT INFORMATION

| PROJECT NAME |  | COURSE PROFESSOR | PROJECT PI/SPONSOR |
| --- | --- | --- | --- |
| DroneRanger Hardware |  | Tehmina Amjad | Ilmi Yoon |
| STUDENT | EMAIL | Expertise |  |
| Jiarui Zha | zha.j@northeastern.edu | Northeastern University |  |

PROJECT OVERVIEW

| PROBLEM OR ISSUE | Low-cost autonomous patrol drones could make residential security affordable, but only if the hardware is safe, reliable, and accurately positioned [1-3]. The Spring 2026 Drone Ranger prototype (Holybro X500 V2, Pixhawk 6C/PX4, Jetson Orin Nano, OAK-D Lite) has flown basic offboard missions, but it still has a power-wiring fire hazard, a fragile flight-controller link, up to 0.5 m altitude error, untested failsafes, and no approved autonomous outdoor flight [4-6]. |
| --- | --- |
| PURPOSE OF PROJECT | The hardware group will harden and integrate the Drone Ranger platform so it flies safely, reliably, and measurably outdoors: a rebuilt power system and flight-controller link, a downward rangefinder and improved GNSS fused in PX4's EKF2 estimator, verified failsafes, and a simulation twin for rehearsal [5-8]. The semester ends with an approved autonomous waypoint patrol over a household garden near the Silicon Valley campus [14-16]. |
| BUSINESS CASE | Security and surveillance drones are a multi-billion-dollar market, estimated to grow 13-20% per year [9-10]. A residential patrol drone system costs about $10k [11], and enterprise patrol drones $15-25k each [12]. Drone Ranger is built from about $1.5k of open parts. A safe, documented, outdoor-validated hardware baseline makes it a reusable testbed for the PI's lab and for the algorithm group's future autonomy work. |
| GOALS / METHODS / METRICS | Goal: Deliver a hardened, outdoor-ready Drone Ranger platform and complete at least one approved autonomous garden-patrol flight by December 2026. Methods: Fused, insulated power distribution; FTDI serial link with a fixed PX4 port map; TFmini Plus rangefinder and relocated GNSS/compass (RTK if funded) fused in EKF2; RC kill switch plus geofence, return-to-launch, battery and link-loss failsafes; PX4 SITL rehearsal before every flight; staged tests from bench to indoor to outdoor O1 (manual) and O2 (PX4 Mission-mode patrol) [6-8], [13]. Metrics: 0 electrical incidents and 0 link drops; 100% of failsafes verified; hover altitude RMSE ≤ 0.15 m (from 0.5 m); waypoint error vs. surveyed ground markers measured and reported (≤ 0.3 m with RTK) [3]; ≥ 1 autonomous outdoor patrol loop (≥ 4 waypoints + return) with no pilot takeover; ≥ 10 min usable flight time. |
| EXPECTED DELIVERABLES | 1. Hardened Platform: Rebuilt power system, RC kill switch, and installed rangefinder, GNSS mast, and Remote ID module, with a wiring diagram and bill of materials. 2. Configuration & Test Toolkit: Versioned PX4 parameter file, SITL digital twin, one-command launch, and post-flight log-analysis scripts. 3. Outdoor Flight Package: Approved flight-safety plan with homeowner permission, pre-flight checklists, compliance records, and O1/O2 flight logs and video. 4. Evaluation Report & Handover: Baseline-vs-final metrics and a handover guide, including the camera/TF interface for the algorithm group. |

PROJECT SCOPE

| WITHIN SCOPE | Hardware repair and integration on the existing X500 V2: power, wiring, flight-controller link, and sensors (TFmini Plus, GNSS/compass, Remote ID; RTK if funded). PX4 configuration (ports, EKF2 sensor fusion, failsafes, geofence), PX4 SITL rehearsal, and flight-log analysis tools. Staged testing: bench → indoor regression → outdoor O1 (manual, at an approved field or the garden) → O2 (autonomous PX4 Mission-mode patrol) over a household garden. Daylight, visual-line-of-sight, low-altitude flights under NU UAS Review Board approval, FAA Part 107 and Remote ID, and California privacy law, with written homeowner permission and a geofence inside the property line [14-16]. A documented depth-camera and TF interface handed to the algorithm group. |
| --- | --- |
| OUTSIDE OF SCOPE | Obstacle-avoidance, mapping, and path-planning algorithms (algorithm group), and ROS 2 offboard autonomy outdoors. Flights beyond visual line of sight, at night, over people, or in controlled airspace without authorization. Multi-drone operation, learning-based control (RL / Isaac Sim), and custom flight-controller firmware. Docking/charging stations, payloads, and product certification. Recording or storing imagery of neighboring properties or bystanders. |

TENTATIVE SCHEDULE

| KEY MILESTONE | START | FINISH |
| --- | --- | --- |
| Form Project Team / Preliminary Review / Scope | 09/28/2026 | 10/04/2026 |
| Finalize Project Plan / Charter / Kick Off | 10/01/2026 | 10/09/2026 |
| Define Phase (requirements, safety plan, UAS Review Board filing) | 10/05/2026 | 10/16/2026 |
| Measurement Phase (power/link rebuild, SITL twin, indoor baseline) | 10/12/2026 | 10/30/2026 |
| Analysis Phase (root causes, EKF2 and failsafe setup) | 10/26/2026 | 11/06/2026 |
| Improvement Phase (sensor integration, outdoor O1 → O2) | 11/02/2026 | 12/04/2026 |
| Control Phase (final metric runs, checklists) | 11/30/2026 | 12/15/2026 |
| Project Summary Report and Close Out | 12/14/2026 | 12/25/2026 |

REFERENCES

[1]	N. Basilico, “Recent trends in robotic patrolling,” Current Robotics Reports, vol. 3, pp. 65–76, 2022, doi: 10.1007/s43154-022-00078-5.

[2]	Y. Chang, Y. Cheng, U. Manzoor, and J. Murray, “A review of UAV autonomous navigation in GPS-denied environments,” Robotics and Autonomous Systems, vol. 170, Art. no. 104533, 2023, doi: 10.1016/j.robot.2023.104533.

[3]	N. Joubert, J. L. E, D. B. Goldman, F. Berthouzoz, M. Roberts, J. A. Landay, and P. Hanrahan, “Towards a drone cinematographer: Guiding quadrotor cameras using visual composition principles,” arXiv:1610.01691, 2016.

[4]	R. Yin, “Drone Project Technical Handover: PX4 / ROS 2 / OAK-D Lite autonomous flight and obstacle-aware planning system,” Northeastern University, internal technical report, 2026.

[5]	NVIDIA, “Jetson Orin Nano Developer Kit Carrier Board Specification,” SP-11324-001_v1.3, Dec. 2024.

[6]	PX4 Autopilot, “PX4 User Guide (v1.17): EKF2, safety and failsafes, RTK GNSS, and Mission mode,” 2026. [Online]. Available: https://docs.px4.io/main/en/

[7]	Benewake, “TFmini Plus LiDAR Module User Manual,” 2024.

[8]	Holybro, “PX4 Development Kit – X500 v2,” 2026. [Online]. Available: https://holybro.com/products/px4-development-kit-x500-v2

[9]	MarketsandMarkets, “Surveillance and Security Drones Market – Global Forecast to 2031,” 2025. [Online]. Available: https://www.marketsandmarkets.com/Market-Reports/surveillance-security-drones-market-43310074.html

[10]	The Business Research Company, “Safety and Security Drones Global Market Report 2026,” 2026. [Online]. Available: https://www.thebusinessresearchcompany.com/report/safety-and-security-drones-global-market-report

[11]	Engadget, “Sunflower’s $9,950 security drone aims to protect your home autonomously,” Jan. 7, 2020. [Online]. Available: https://www.engadget.com/2020-01-07-sunflower-residential-security-drone.html

[12]	DroneXL, “Skydio X10: Specs, price, DFR programs and the X10D (2026),” 2026. [Online]. Available: https://dronexl.co/drone-companies/skydio/skydio-x10/

[13]	A. Jacoff et al., “Standard Test Methods for Small Unmanned Aircraft Systems: Maneuvering (MAN 1-5) and Payload Functionality (PAY 1-5),” NIST / ASTM E54.09, 2019.

[14]	Federal Aviation Administration, “14 CFR Part 107: Small Unmanned Aircraft Systems” and “Remote Identification of Drones,” 2026. [Online]. Available: https://www.ecfr.gov/current/title-14/chapter-I/subchapter-F/part-107

[15]	Northeastern University, “Policy 615: Use of Unmanned Aircraft Systems” and “sUAS Guidelines,” rev. Sep. 30, 2025. [Online]. Available: https://policies.northeastern.edu/policy615

[16]	California Civil Code §1708.8, “Physical invasion of privacy” (airspace provision added by AB 856, 2015). [Online]. Available: https://leginfo.legislature.ca.gov/faces/codes_displaySection.xhtml?lawCode=CIV&sectionNum=1708.8